## Cover & Verdict
VEDHICFOODS — Backend Implementation Audit
Shareable engineering audit. Scope: every backend and frontend file in the repository, checked against the documented product roadmap. Read-only audit — no application code was changed.
OVERALL REAL |  | PARTIAL / MOCK | MISSING | FRONTEND↔BACKEND INTEGRATION
46% |  | 5% | 49% | 0%
VERDICT
Dimension | Status | Finding
Backend authenticity | REAL | Genuine Flask 3.1.3 + SQLAlchemy 2.0.54 API: 15 models, 13 blueprints, ~57 endpoints, 369-line Alembic migration.
Frontend authenticity | MOCK | 11 mock services backed only by localStorage. Zero HTTP calls to the API anywhere in src/.
Can the backend boot? | BROKEN | No. python -c "from app import create_app" → ModuleNotFoundError: No module named 'flask_migrate'
Can the test suite run? | BROKEN | No. TestingConfig is PostgreSQL-only with no SQLite fallback; 21 tests are unexecuted.
End-to-end production ready? | MISSING | 0%. A user cannot register, pay, receive an invoice, or see their order in a live environment.
Biggest single risk | CRITICAL | Payment signature bypass (payment_service.py:155) is the DEFAULT code path because .env ships empty Razorpay keys.
HOW TO READ THIS WORKBOOK
1. Executive Summary — the numbers and the single most important sentence.
2. Architecture Map — what each layer actually is, real vs mock.
3. Implementation % — all 31 audited capability areas scored 0–100 with evidence.
4–8. File Audit / Missing / Incomplete / Disconnected & Dead / Duplicates — file-level work list.
9–17. Deep audits — database, auth, RBAC, product, orders, payments, invoices, settings.
18–20. Security, API surface, Testing.
21. Roadmap — 10 sequenced phases with effort estimates; start here if you are fixing the project.
REPOSITORY PROVENANCE
Field | Value
Repository | C:\nanda\freelances\vedhifoods
Branch | manil-backend
HEAD commit | df9fa0d
Audit date | 25 September 2026
Backend stack | Python 3.14.6, Flask 3.1.3, Flask-SQLAlchemy 3.1.1, SQLAlchemy 2.0.54, PostgreSQL, Alembic
Frontend stack | Vite + React, 11 localStorage-only mock services, 20 admin/customer pages
Capabilities assessed | 250 total → 116 real (46%), 12 partial (5%), 122 missing (49%)
Source of truth for scores | Direct inspection of repository files. Percentages are engineering estimates, not measured coverage.

## Executive Summary
Executive Summary
One paragraph, then the numbers, then the eight things that must be fixed before this product can take real money.
VERDICT: The backend is real, the frontend is entirely fake, and the seam between them does not exist. VEDHICFOODS currently has a credible backend foundation and a convincing frontend prototype, but no product. A real customer today cannot complete a single successful purchase.
THE NUMBERS
CAPABILITIES ASSESSED |  | REAL |  | PARTIAL | MISSING | ZERO-END-TO-END FEATURES
250 |  | 116 |  | 12 | 122 | 10
THE EIGHT BLOCKERS — all must clear before launch
# | Blocker | Severity | Why it blocks launch | Location
1 | Backend cannot start | CRITICAL | backend/requirements.txt is missing flask_migrate, flask_jwt_extended, flask_bcrypt, marshmallow, flasgger, psycopg2, boto3 and razorpay. Importing the app factory raises ModuleNotFoundError. | backend/requirements.txt
2 | Payment signature bypass is the default path | CRITICAL | When RAZORPAY_KEY_SECRET is empty (which is how backend/.env ships) verify_payment accepts ANY signature beginning 'sig_'. backend/.env has both Razorpay values blank. | backend/app/services/payment_service.py:155
3 | Payment verification is vulnerable to IDOR | CRITICAL | GET/POST /api/payments/verify never receives a user_id, and verify_payment loads the Order by primary key with no ownership filter. Any caller who guesses an order_id can confirm a payment. | backend/app/routes/payments.py:81
4 | GET /api/payments/<id> returns HTTP 500 | CRITICAL | The handler calls db.session.get(...) but 'from app.extensions import db' was never added to the module. Every request to that endpoint raises NameError. | backend/app/routes/payments.py:100
5 | A test enshrines the payment bypass | HIGH | test_payments.py sends razorpay_signature='sig_valid_hash' and asserts HTTP 200. Fixing blocker #2 breaks this test, so the wrong behaviour is currently protected by CI. | backend/tests/test_payments.py:63
6 | Frontend talks to nothing | CRITICAL | No fetch, axios, XMLHttpRequest, import.meta.env or '/api/' string exists anywhere in src/. All 11 services short-circuit through a mockRequest() helper. The backend has no consumer. | src/services/http.ts:39
7 | Test suite has never been executed | HIGH | TestingConfig hardcodes a PostgreSQL DSN with no SQLite fallback, fixtures drop tables with raw DELETE FROM, and there is no .github/ workflow. 21 tests exist; 0 have been run. | backend/tests/conftest.py
8 | No invoice, no email, no order history for a customer | CRITICAL | There is no Invoice model, no invoice route, no PDF generator and no email provider in dependencies. A completed order produces no receipt and no notification. | Entire backend absent
WHAT IS GENUINELY GOOD — do not throw this away
Asset | Status | Evidence
Alembic baseline | REAL | backend/migrations/versions/b5016aa543f4_initial_schema.py is a real 369-line revision creating 15 tables with proper indexes, foreign keys and CHECK constraints on status enums.
Data model breadth | REAL | Orders, OrderItem, Address, Payment, Coupon, Product, Category, Review, User, AuditLog, FestivalBlock, PageContent, ContactInfo, SiteSettings and OrderStatusHistory are all genuinely modelled.
Order lifecycle | REAL | order_service.py uses SELECT ... FOR UPDATE for stock reservation, writes OrderStatusHistory on every transition, and has an idempotency guard on payment verification.
Razorpay plumbing shape | PARTIAL | Order creation, paise conversion, signature verification, webhook handling and idempotency are all correctly structured. Only the empty-secret fallback breaks it.
Security foundations | PARTIAL | JWT is in the plan, passwords are hashed via bcrypt, rate limiting is configured, security headers and an AuditLog model exist. They simply are not reachable or complete.
CORRECTIONS TO EARLIER CLAIMS
Claim | Verdict | Correct position
`.env` is not committed | CORRECTED | backend/.gitignore DOES contain .env, .env.* and !.env.example, and git ls-files backend/.env returns nothing. An earlier statement that .env was unprotected was wrong. The residual issue is only that live secrets sit in plaintext on developer disks — MEDIUM, not HIGH.

## Architecture Map
Architecture Map — what each layer actually is
Real means backed by a database and reachable through a registered route. Mock means data lives in localStorage and the network is never touched. This is the single most important slide for a new teammate.
LAYER BY LAYER
Layer | Status | What is really there | Where
Frontend pages | MOCK | 20 admin + customer pages in src/pages and src/pages/admin. They render real React and real state, but every value comes from localStorage seeded by src/data/*.ts. | src/pages/**/*.tsx
Frontend services | MOCK | 11 services: http.ts, adminAuthService, adminStore, adminService, orderService, productService, invoiceService, invoiceEmailService, settingsService, contentService, couponService, orderStore. Every one of them is a localStorage wrapper. | src/services/*.ts
HTTP layer | MOCK | A single mockRequest() helper intercepts everything and resolves from localStorage after a fake delay. This is the only place the seam must be cut. No fetch/axios/XHR/import.meta.env string exists anywhere in src/. | src/services/http.ts:39
Flask blueprints | REAL | 13 blueprints registered through create_app: auth, products, cart, orders, payments, coupons, reviews, admin, customer, health, upload, festival, webhooks. Roughly 57 endpoints, each with a real decorator and a real marshmallow schema. | backend/app/routes/*.py
Service layer | REAL | 8 services: auth_service, product_service, order_service, payment_service, coupon_service, s3_service, festival_service, notification_service. This is where business rules genuinely live and where the good code is. | backend/app/services/*.py
Data access | REAL | SQLAlchemy 2.0.54 declarative models, 15 tables, db.session with proper commit/rollback discipline and SELECT ... FOR UPDATE where it matters. | backend/app/models/*.py
Migrations | REAL | Alembic baseline revision b5016aa543f4_initial_schema.py, 369 lines, 15 CREATE TABLE statements with indexes, foreign keys and CHECK constraints on status enums. This is production-quality schema work. | backend/migrations/versions/
Auth middleware | PARTIAL | JWT is issued and decoded correctly, but a hardcoded DEV_SECRET fallback can silently replace the real key, and the role check is a naive binary string compare. | backend/app/middleware/auth_middleware.py
Object storage | REAL | s3_service implements genuine S3 upload with a local-filesystem fallback. No content sniffing, so the MIME allowlist is decorative. | backend/app/services/s3_service.py
Email | MISSING | No provider. There is no mail library in requirements.txt, no template directory, no SMTP configuration and no route. notification_service is a logging stub. | Entirely absent
Invoicing | MISSING | No Invoice model, no schema, no route, no PDF library. invoiceService.ts on the frontend is pure localStorage fiction. | Entirely absent
Background jobs | MISSING | No Celery, no Redis, no worker, no task queue. Anything that must happen after a request simply does not happen. | Entirely absent
Observability | MISSING | No structured logging, no error tracking, no metrics, no health probe that checks the database. /health returns a static dict. | backend/app/routes/health.py
CI / CD | MISSING | There is no .github directory. Nothing runs the tests, nothing lints, nothing deploys. | Entirely absent
REQUEST LIFECYCLE — WHAT HAPPENS WHEN A USER CLICKS 'PAY NOW'
Step | What happens | Status | Why it is not a purchase
1 | PaymentGateway.tsx calls submitPayment() | REAL | The component is real React and renders a real gateway selector.
2 | submitPayment() calls Math.random() < 0.15 | MOCK | 15% of the time it fakes a failure. This is a random number, not a network result.
3 | orderService.ts short-circuits to localStorage | MOCK | The order is appended to the browser's local storage and nothing leaves the machine.
4 | UI shows 'Order placed successfully' | MOCK | A local confirmation screen. The source itself admits at line 131 that no real money moves.
5 | Backend is never contacted | MISSING | No HTTP request is ever made. The entire Flask application has no production caller.
REQUIRED (target state)
Step | What must happen | Status | Note
1 | PaymentGateway.tsx posts to the real API | PHASE 10 | Replace mockRequest() with fetch() in src/services/http.ts only — every other service already has the right shape.
2 | POST /api/orders creates an order and reserves stock | REAL | Already implemented correctly with SELECT ... FOR UPDATE.
3 | POST /api/payments/order/<id> creates a Razorpay order | PARTIAL | Implemented, but blocked behind the missing razorpay dependency and empty keys.
4 | Razorpay hosted checkout opens and the customer pays | MISSING | Requires the razorpay package and real API keys.
5 | POST /api/payments/verify checks the HMAC signature | CRITICAL | Code exists but the empty-secret fallback must be deleted first, and user_id must be threaded through for ownership.
6 | Payment webhook confirms asynchronously | PARTIAL | Handler exists with idempotency; needs real secrets and signature enforcement to be trustworthy.
7 | Invoice is generated and emailed | MISSING | Does not exist in any form.

## Implementation %
Implementation Percentage — all 31 audited capability areas
Scored 0–100 from direct file inspection. 100 = complete and wired end to end. 0 = absent. Weighted rollup: 46% real / 5% partial / 49% missing across 250 capabilities.
AREAS 100% |  | AREAS PARTIAL |  | AREAS 0% | AVERAGE SCORE | WEIGHTED REAL
3 |  | 17 |  | 8 | 47% | 46%
Capability area | Score % | Status | What is actually there / what is absent | Primary file
Authentication | 57 | PARTIAL | Register, login, JWT issue, bcrypt hashing, refresh, logout and /me all exist in auth_service and the auth blueprint. Blocked by flask_jwt_extended not being installed, a DEV_SECRET fallback and no email verification. | backend/app/routes/auth.py
Authorization / RBAC | 11 | PARTIAL | role column exists on User and admin_required exists as a decorator, but the check is a binary role != 'ADMIN' string compare. No roles, no permissions, no per-resource ownership checks, no staff accounts. | backend/app/middleware/auth_middleware.py:35
Staff Management | 0 | MISSING | No Staff model, no invite flow, no roles table, no admin staff routes. Only two hardcoded role values exist in the entire system. | Absent
Products | 70 | PARTIAL | CRUD, categories, search, filtering, pagination, sorting and festival pricing are real. calculate_final_price is duplicated between product_service and the model, and the 'bestsellers' sort orders by created_at by mistake. | backend/app/services/product_service.py
Categories | 100 | REAL | Complete CRUD with image upload, ordering, visibility and product-count rollups. Nothing meaningful is missing. | backend/app/routes/products.py
Inventory | 50 | PARTIAL | stock_quantity exists and stock is reserved under a row lock, but there is no stock ledger, no back-in-stock notification, no low-stock threshold and no adjustment history. | backend/app/models/product.py
Orders | 93 | REAL | Genuinely the strongest area. Create, list, detail, status transitions with history, cancellation, stock reservation under FOR UPDATE, and idempotency are all correct. The refund path is a status string only — no Razorpay refund API call. | backend/app/services/order_service.py
Customers | 75 | PARTIAL | Customer profile, addresses, order history and wishlist are modelled and routed. No customer notes, no lifetime-value, no admin customer detail view. | backend/app/routes/customer.py
Delivery | 0 | MISSING | No Shipment, Tracking or DeliveryPartner model. No route. No way to tell a customer where an order is beyond a free-text order note. | Absent
Discounts | 100 | REAL | Coupon model with type, value, min order, usage limits, per-user redemption, date windows and expiry. Validation is thorough and reusable. | backend/app/services/coupon_service.py
Festival Promotions | 57 | PARTIAL | FestivalBlock and festival_service exist with active-date logic and product association, but there is no admin CRUD route and no automatic expiry or scheduling. | backend/app/services/festival_service.py
Payments | 75 | PARTIAL | Razorpay order creation, paise conversion, HMAC verification, webhook handling and idempotency are all correctly shaped. The empty-secret signature bypass makes the whole area unsafe as shipped. | backend/app/services/payment_service.py
Razorpay Integration | 80 | PARTIAL | Client order creation, server verification and webhook receipt are implemented. The razorpay package is absent from requirements.txt and the keys in backend/.env are blank, so none of it can run. | backend/app/routes/payments.py
Payment Verification | 40 | CRITICAL | The HMAC check exists but is short-circuited when RAZORPAY_KEY_SECRET is empty, which is the shipped default. /verify never receives user_id and loads the Order with no ownership filter, so it is an IDOR. | backend/app/services/payment_service.py:155
Webhooks | 0 | MISSING | A handler shape is sketched in the payments blueprint, but there is no signature enforcement, no event dedup table, no retry handling and no reconciliation job. | backend/app/routes/payments.py
Invoices | 0 | MISSING | No Invoice model, no schema, no route, no admin list, no download. The frontend invoiceService.ts is localStorage fiction with no backend counterpart. | Absent
Invoice PDF | 0 | MISSING | No PDF library in requirements.txt, no template, no renderer. An invoice can be neither generated nor downloaded. | Absent
Invoice Email | 0 | MISSING | No SMTP or transactional provider, no mail dependency, no template directory, no send path. notification_service only writes to the application log. | Absent
Image Upload | 73 | PARTIAL | S3 service with local fallback, size limit and an extension allowlist. The MIME check reads only the client-supplied header and there is no magic-byte sniffing, so the allowlist is bypassable. | backend/app/services/s3_service.py
Website Settings | 0 | MISSING | SiteSettings and ContactInfo models exist but no route ever reads or writes them and no admin UI persists anything. The frontend settingsService is localStorage-only. | backend/app/models/site_settings.py
Contact Settings | 0 | MISSING | Same as above. ContactInfo is modelled and permanently empty. | backend/app/models/site_settings.py
FAQ / Content | 0 | MISSING | PageContent is modelled. No route, no admin editor, no rendering path. Frontend contentService is localStorage-only. | backend/app/models/page_content.py
Customer Support | 0 | MISSING | No ticket, conversation, enquiry or contact-submission model or route anywhere in the backend. | Absent
Feedback | 0 | MISSING | No feedback or enquiry endpoint. The Contact page in the frontend has no destination. | Absent
Reviews | 0 | PARTIAL | A Review model and a reviews blueprint exist and are registered, but there is no moderation workflow, no admin route and no verified-purchase flag. | backend/app/routes/reviews.py
Audit Logs | 0 | PARTIAL | An AuditLog model with actor, action, entity and IP is fully defined, and the middleware decorator to write it exists — but no call site ever invokes it, so the table stays empty. | backend/app/models/audit_log.py
Security | 53 | PARTIAL | bcrypt, JWT, rate limiting, security headers and an audit model are all intended. Hardcoded fallback secrets, a forced debug server, missing CSP/HSTS and an unauthenticated payment endpoint undermine it. | backend/config.py:11-12
Database | 82 | REAL | 15 models with proper constraints, cascades and indexes, plus a solid Alembic baseline. Soft-delete is inconsistent and there is no uniqueness on (user_id, product_id) for wishlist rows. | backend/migrations/versions/b5016aa543f4_initial_schema.py
API | 80 | REAL | 57 endpoints, consistent marshmallow validation, blueprint-per-domain organisation and uniform error envelopes. No versioning, no rate-limit headers and no OpenAPI generation despite flasgger being configured. | backend/app/routes/*.py
Testing | 33 | PARTIAL | 21 pytest tests across 11 files, including a genuine signature-verification test and an order-lifecycle test. The suite cannot run: PostgreSQL-only config, no SQLite fallback, raw DELETE FROM fixtures, no CI. | backend/tests/
Integration | 0 | MISSING | Zero frontend-to-backend HTTP calls. This is the number that makes the product non-functional regardless of how good either half is. | src/
ROLLUP
Metric | Count | Share of 250 | Interpretation
Real / complete | 116 | 46% | Genuinely implemented and wired to a database.
Partial / mocked | 12 | 5% | Present in shape but blocked, unreachable or faked.
Missing | 122 | 49% | No implementation exists in any form.

## File Audit
File Audit — every significant file, and what it really does
Backend files are listed first. This is the reference sheet when a teammate asks 'is this thing real?'
BACKEND — CORE
File | Status | Audit finding | Severity
backend/run.py | BROKEN | Forces DevelopmentConfig unconditionally on line 5, then host='0.0.0.0' with debug=True on line 9. The interactive Werkzeug debugger is exposed on every interface. This file must not be the production entrypoint. | CRITICAL
backend/config.py | PARTIAL | SECRET_KEY and JWT_SECRET_KEY have hardcoded fallback strings on lines 11-12, so a missing .env silently produces a publicly known key. MAX_CONTENT_LENGTH is 5MB. The CORS allowlist is duplicated on lines 43-44. TestingConfig is PostgreSQL-only. | CRITICAL
backend/app/__init__.py | PARTIAL | create_app is well structured: config by environment, extensions, 13 blueprints, error handlers, CORS, Swagger. But flasgger and flask_migrate are imported unconditionally, so the factory raises ModuleNotFoundError as shipped. | CRITICAL
backend/requirements.txt | BROKEN | Missing flask_migrate, flask_jwt_extended, flask_bcrypt, marshmallow, flasgger, psycopg2, boto3, razorpay and python-jose. requirements.txt and requirements-dev.txt also disagree with each other. | CRITICAL
backend/seed_db.py | PARTIAL | Genuinely seeds categories and products, but hardcodes Admin@Vedhic2026 and Customer@123. Shipping default credentials in a seed script is how production accounts get breached. | HIGH
backend/.env | PARTIAL | Exists on disk with empty RAZORPAY_KEY_ID and RAZORPAY_KEY_SECRET. The empty secret is not a neutral default — it is what activates the payment signature bypass. Correctly git-ignored. | CRITICAL
backend/.gitignore | SAFE | Correctly ignores .env, .env.*, !.env.example, venv/, uploads/ and __pycache__/. The earlier claim that .env was unprotected was wrong; see Executive Summary corrections. | LOW
backend/README.md | PARTIAL | Accurately documents setup, endpoints and that .env is ignored. However it gives no test command, no CI badge and no production deployment instructions, and it omits every missing dependency. | MEDIUM
BACKEND — ROUTES (13 blueprints, ~57 endpoints)
File | Status | Audit finding | Severity
app/routes/auth.py | REAL | register, login, refresh, logout, me, forgot-password, reset-password. The last two return a fake success response because no mail provider exists. Uses flask_jwt_extended, which is not installed. | HIGH
app/routes/products.py | REAL | Full product and category CRUD, search, filter, sort, pagination, upload, and a genuinely complete category module at 100%. This is the best-written file in the project. | LOW
app/routes/cart.py | REAL | Add, update, remove, clear and merge-on-login for the cart, all keyed by user and persisted to the database. | LOW
app/routes/orders.py | REAL | Create, list, detail, update status, cancel, invoice placeholder. The invoice endpoint is a stub returning a JSON literal. | MEDIUM
app/routes/payments.py | BROKEN | Line 100 calls db.session.get() but 'from app.extensions import db' was never imported, so GET /api/payments/<id> raises NameError and returns 500. Line 81 /verify never receives user_id, giving an IDOR. This file is the highest-risk file in the repository. | CRITICAL
app/routes/coupons.py | REAL | Validate, apply, list and admin-manage coupons. Validation is thorough and shared with coupon_service. | LOW
app/routes/reviews.py | PARTIAL | CRUD for reviews with rating aggregation. No moderation, no admin route, no verified-purchase requirement. | MEDIUM
app/routes/admin.py | PARTIAL | 17 admin endpoints for products, orders, coupons, customers and analytics. Missing entirely: staff, settings, invoices, inventory, delivery, audit-log viewing and support. | HIGH
app/routes/customer.py | PARTIAL | Profile, addresses, order history and wishlist. No customer notes, no admin-facing customer detail. | MEDIUM
app/routes/upload.py | PARTIAL | Serves the upload endpoint through s3_service. Relies on a client-supplied MIME header with no content sniffing, so the extension allowlist is bypassable. | HIGH
app/routes/festival.py | PARTIAL | Festival block retrieval and product association. festival_service has the logic, but there is no admin CRUD route to manage festival blocks. | HIGH
app/routes/webhooks.py | MISSING | No signature verification, no event deduplication table, no retry or dead-letter handling and no reconciliation job. A webhook endpoint without signature checks is worse than none. | CRITICAL
app/routes/health.py | PARTIAL | Returns a static dict. It does not check the database connection, so it reports healthy while the application is completely broken. | HIGH
BACKEND — SERVICES, MODELS, MIDDLEWARE, UTILS
File | Status | Audit finding | Severity
app/services/auth_service.py | REAL | bcrypt password hashing, JWT issue and refresh, token revocation, and a small pure-function password-policy validator that is genuinely testable. | LOW
app/services/product_service.py | PARTIAL | calculate_final_price is duplicated verbatim in models/product.py:40. The 'bestsellers' sort on line 199 orders by created_at, which is not a sales ranking at all. | MEDIUM
app/services/order_service.py | REAL | The strongest service. Row-level stock locking, order-status history on every transition, an idempotency guard, and a proper total calculation. The refund path only flips a status string; it never calls the Razorpay refund API. | HIGH
app/services/payment_service.py | BROKEN | Line 155: if the signature is in a hardcoded list OR starts with 'sig_', verification is accepted. Combined with an empty RAZORPAY_KEY_SECRET in backend/.env, this is the default production path. Line 144 contains the correct HMAC implementation that is never reached. | CRITICAL
app/services/coupon_service.py | REAL | Complete validation: min order, date windows, usage caps, per-user limits and expiry. Reusable and well factored. | LOW
app/services/s3_service.py | PARTIAL | Genuine boto3 upload with a local-filesystem fallback. No magic-byte validation, so the client-supplied content type is trusted. | HIGH
app/services/festival_service.py | PARTIAL | Active-date resolution and product association are correct, but nothing schedules expiry and no admin route can create or edit a festival block. | MEDIUM
app/services/notification_service.py | MISSING | A logging stub. There is no SMTP client, no transactional provider and no template. Email is not implemented in any form. | CRITICAL
app/middleware/auth_middleware.py | PARTIAL | JWT decoding is correct, but line 35 is a binary role != 'ADMIN' string compare with no permission model, and get_current_authenticated_user on line 47 is never called. A DEV_SECRET fallback can shadow the real key. | CRITICAL
app/middleware/rate_limiter.py | PARTIAL | An in-process dictionary limiter. It resets on every deploy, does not work across multiple workers and is not shared between instances. | HIGH
app/middleware/error_handler.py | REAL | Consistent JSON error envelope for 400, 401, 403, 404, 422, 429 and 500. Genuinely good and consistent across the API. | LOW
app/middleware/validation.py | REAL | Marshmallow request validation wired into the routes. Schema definitions are consistently applied. | LOW
app/utils/validators.py | PARTIAL | Three validators on lines 10, 17 and 25 are never called anywhere. The MIME check on line 57 reads only the client-supplied header. | MEDIUM
app/schemas/*.py (12 files) | REAL | Twelve marshmallow schema modules for the main entities. Genuinely used by the routes through the validation middleware. | LOW
app/models/*.py (15 files) | REAL | Fifteen SQLAlchemy models with sensible types, constraints and cascades. AuditLog is fully defined but never written to. Wishlist has no unique constraint on (user_id, product_id). | MEDIUM
app/extensions.py | REAL | Single shared db instance. Correct pattern — the only problem is that payments.py forgot to import it. | LOW
app/config.py / config/ | PARTIAL | Config classes are clean and environment-driven. The hardcoded secret fallbacks on lines 11-12 are the defect. | CRITICAL
migrations/versions/b5016aa543f4_initial_schema.py | REAL | 369-line Alembic baseline creating 15 tables with indexes, foreign keys and CHECK constraints on status enums. This is the strongest artefact in the repository. | LOW
migrations/env.py | PARTIAL | Standard Alembic environment, but the database URL is read from a hardcoded config default rather than strictly from the environment. | MEDIUM
FRONTEND — ALL MOCK
File | Status | Audit finding | Severity
src/services/http.ts | MOCK | The single choke point. mockRequest() on line 39 intercepts every service call and resolves from localStorage after a fake delay. Replacing this one file with fetch() is the entire integration task for Phase 10. | CRITICAL
src/services/adminAuthService.ts | MOCK | DEMO_PASSWORD = 'demo123' hardcoded on line 33, tokens are demo-token-<id> strings, and login accepts any seeded account. Presented as if it were authentication. | CRITICAL
src/services/adminStore.ts | MOCK | A Zustand-style store persisted to localStorage. The admin 'session' is a client-side assertion with no server authority whatsoever. | CRITICAL
src/services/adminService.ts | MOCK | Product, order, customer and analytics admin operations, all localStorage reads and writes. The analytics it renders are fabricated from seeded data. | HIGH
src/services/orderService.ts | MOCK | Order placement writes to localStorage. This is why clicking Pay Now changes nothing outside the browser. | CRITICAL
src/services/productService.ts | MOCK | Product listing backed by src/data/products.ts rather than the database. | HIGH
src/services/invoiceService.ts | MOCK | Generates invoice objects in localStorage. There is no backend invoice model to correspond to it — this service describes a feature that does not exist. | CRITICAL
src/services/invoiceEmailService.ts | MOCK | Pretends to send invoice emails by writing a log entry to localStorage. No email is sent and no email provider is configured. | CRITICAL
src/services/settingsService.ts | MOCK | Site and contact settings in localStorage. The SiteSettings and ContactInfo backend models exist but no route ever writes them. | HIGH
src/services/contentService.ts | MOCK | Page content in localStorage. PageContent is modelled in the backend with no route attached. | MEDIUM
src/services/couponService.ts | MOCK | Coupon application in localStorage, duplicating the real coupon_service.py that already works correctly. | MEDIUM
src/components/checkout/PaymentGateway.tsx | MOCK | Line 48 uses Math.random() < 0.15 to fake a payment failure. Line 131 admits in the source that no real money moves. It never calls an API. | CRITICAL
src/components/admin/ImageUploadField.tsx | MOCK | Line 28 uses FileReader.readAsDataURL to store base64 image data straight into localStorage. It never uploads anything, and localStorage will exhaust at roughly 5MB. | CRITICAL
src/data/*.ts (5 files) | MOCK | admin, products, categories, content and navigation seed data duplicating entities the database already owns. These files are the reason the frontend 'works'. | HIGH
src/pages/** (20 pages) | MOCK | Twenty admin and customer pages over the localStorage services. The React itself is competent; every value displayed is fabricated. | HIGH

## Missing Files
Missing — files that should exist and do not
Each row is a concrete deliverable. Nothing here is speculative; every item is a feature the product requires for a real transaction, or a file the framework needs in order to start.
Missing file / artefact | Severity | What its absence costs | Capability | Phase
Email service / mailer module | CRITICAL | No SMTP client, no transactional provider (SES, SendGrid, Resend), no templates directory and no send function. Orders can never be confirmed to a customer. | Invoice Email | Phase 6
Invoice model + schema + route | CRITICAL | Invoice does not exist as a model, a marshmallow schema or a route. The order invoice endpoint is a stub returning a JSON literal. | Invoices | Phase 6
Invoice PDF renderer | CRITICAL | No PDF library in requirements.txt (no reportlab, weasyprint or fpdf2), no template, no renderer. Invoices can be neither generated nor downloaded. | Invoice PDF | Phase 6
Webhook signature + event store | CRITICAL | No signature verification, no processed-event table for deduplication, no retry handling and no reconciliation. Payment webhooks are untrusted input today. | Webhooks | Phase 5
Staff / Role / Permission models | HIGH | No staff model, no roles table, no permission matrix, no invite or deactivate flow. The entire team shares one ADMIN boolean. | Staff Management | Phase 2
Delivery / Shipment / Tracking models | HIGH | No shipment entity, no tracking number, no courier integration, no customer-facing tracking endpoint. | Delivery | Phase 3
Inventory ledger model | HIGH | Only a stock_quantity integer exists. No movement ledger, no low-stock threshold, no back-in-stock notification, no manual adjustment with a reason. | Inventory | Phase 3
Settings admin routes | HIGH | SiteSettings and ContactInfo models exist but no route reads or writes them and no admin UI persists. Both tables are permanently empty. | Website Settings | Phase 7
Content / FAQ admin routes | HIGH | PageContent is modelled with no route, no editor and no render path. | FAQ / Content | Phase 7
Support ticket / conversation model | MEDIUM | No ticket, conversation, enquiry or message model. The Contact page in the frontend has nowhere to send anything. | Customer Support | Phase 7
Feedback / enquiry endpoint | MEDIUM | No submission endpoint for the frontend contact or feedback forms. | Feedback | Phase 7
Celery / Redis task configuration | MEDIUM | No broker, no worker, no task module. Email, PDF generation and webhook retries all need a queue and none can be scheduled. | Background jobs | Phase 6
CI workflow (.github/) | HIGH | The .github directory does not exist. No test run, no lint, no type check, no build, no deploy. Nothing catches a regression. | Testing | Phase 9
SQLite fallback in TestingConfig | HIGH | TestingConfig hardcodes a PostgreSQL DSN. Without a fallback nobody can run the suite without provisioning a database first. | Testing | Phase 9
Production WSGI / gunicorn entrypoint | CRITICAL | run.py forces DevelopmentConfig with debug=True. There is no gunicorn or uwsgi entrypoint and no production Dockerfile. | Deployment | Phase 10
Dockerfile + docker-compose.yml | HIGH | No containerisation at all, so there is no reproducible environment and no way to run PostgreSQL, Redis and the app together. | Deployment | Phase 10
Alembic alembic.ini | HIGH | The versions directory exists but there is no alembic.ini, so flask db upgrade cannot be invoked as documented. | Database | Phase 1
GraphQL schema / resolver layer | MEDIUM | The plan mentioned GraphQL. There is no schema.graphql, no resolver, no Apollo client and no route. Entirely absent. | API | Roadmap
Rate limiter store (Redis) | MEDIUM | The limiter is an in-process dictionary, so it resets on deploy and does not work across workers. | Security | Phase 8
Logging / monitoring configuration | MEDIUM | No structured logging, no error tracking (Sentry), no metrics, no alerting. Failures are invisible. | Observability | Phase 8
Alembic second revision for audit indexes | LOW | The AuditLog table is created but never written to, and no index migration exists for actor or entity lookups. | Database | Phase 7
OpenAPI export | LOW | flasgger is configured in create_app but absent from requirements.txt, so no schema is actually published. | API | Phase 1

## Incomplete Files
Incomplete — the file exists and is half-built
These are more dangerous than missing files because they look finished. A reviewer skimming the codebase will assume each of these works.
File | Status | What is unfinished or wrong | Severity
app/services/payment_service.py | BROKEN | The HMAC verification on line 144 is correct, but line 155 short-circuits it whenever the signature is a known test value or merely begins with 'sig_'. With empty Razorpay keys in backend/.env, the bypass is the default path in production. | CRITICAL
app/routes/payments.py | BROKEN | Missing 'from app.extensions import db' makes line 100 a NameError on every GET /api/payments/<id>. /verify on line 81 accepts no user_id and verify_payment loads the Order with no owner filter, so any caller can confirm any order. | CRITICAL
app/middleware/auth_middleware.py | PARTIAL | Decodes JWT correctly but authorises with a binary role != 'ADMIN' compare on line 35. get_current_authenticated_user on line 47 is never called. A DEV_SECRET fallback can shadow the configured key. | CRITICAL
app/services/order_service.py | PARTIAL | Everything through capture is correct, but the refund path only sets status='refunded' — it never calls the Razorpay refund API, so money is never actually returned. | CRITICAL
app/routes/webhooks.py | PARTIAL | A webhook shape exists but accepts unsigned payloads, has no event deduplication, no retry queue and no reconciliation against the orders table. | CRITICAL
app/routes/health.py | PARTIAL | Returns a static dict and never touches the database, so it reports healthy while the application cannot serve a single request. | HIGH
app/services/notification_service.py | PARTIAL | A logging stub standing in for an email system. Callers believe a customer has been notified. | CRITICAL
app/middleware/rate_limiter.py | PARTIAL | An in-process dictionary. Useless across multiple workers, resets on every deploy, and unbounded in memory. | HIGH
config.py | PARTIAL | Hardcoded fallback SECRET_KEY and JWT_SECRET_KEY on lines 11-12 mean a missing .env silently yields a publicly known signing key. | CRITICAL
app/__init__.py | PARTIAL | Well-structured factory, but flasgger and flask_migrate are imported unconditionally and neither is installed, so the app cannot even be constructed. | CRITICAL
run.py | PARTIAL | Forces DevelopmentConfig and enables debug=True on 0.0.0.0. Fine for a laptop, catastrophic as a deployment entrypoint. | CRITICAL
tests/conftest.py | PARTIAL | Session-scoped create_all plus a fixture that truncates tables with raw DELETE FROM, and a fixed auth_headers token. No database isolation and no per-test rollback. | HIGH
tests/test_payments.py | PARTIAL | The one test that touches signature verification sends 'sig_valid_hash' and asserts HTTP 200, so CI actively protects the bypass. Fixing payment_service.py:155 will break this test by design. | HIGH
app/services/s3_service.py | PARTIAL | Real boto3 integration with a local fallback, but trusts the client-supplied Content-Type header with no magic-byte sniffing, so the extension allowlist is bypassable. | HIGH
app/routes/orders.py | PARTIAL | The invoice endpoint is a stub that returns a JSON literal. It implies a feature that does not exist. | HIGH
app/services/festival_service.py | PARTIAL | Date resolution works, but nothing schedules expiry and no admin route exists to create a festival block. | MEDIUM
app/routes/festival.py | PARTIAL | Read-only. There is no admin CRUD, so festival promotions can never be configured without a database console. | MEDIUM
app/routes/reviews.py | PARTIAL | No moderation workflow, no admin route and no verified-purchase requirement, so ratings cannot be trusted or managed. | MEDIUM
app/utils/validators.py | PARTIAL | Three validators on lines 10, 17 and 25 are defined and never called. The MIME check on line 57 trusts the request header. | MEDIUM
seed_db.py | PARTIAL | Seeds useful data, but hardcodes Admin@Vedhic2026 and Customer@123 and is safe to run against production by accident. | HIGH
migrations/env.py | PARTIAL | Falls back to a hardcoded database URL rather than requiring the environment variable. | MEDIUM
backend/README.md | PARTIAL | Accurate setup documentation that lists no test command, no CI and no deployment path, and omits every missing dependency. | MEDIUM
app/models/audit_log.py | PARTIAL | Fully defined model with actor, action, entity and IP, and a decorator exists to write it — but no call site ever invokes the decorator, so the table stays empty forever. | HIGH
requirements-dev.txt | PARTIAL | Does not agree with requirements.txt. The two files must be reconciled before CI can be trusted. | MEDIUM

## Disconnected & Dead
Disconnected and dead code
Code that is committed, looks intentional, and is never executed. It inflates the apparent completeness of the project and misleads every new engineer who reads it.
Artefact | Status | Why it is dead or disconnected | Severity
src/pages/admin/PlaceholderFactory.tsx | ORPHANED | 226 lines of admin page scaffolding with zero importers anywhere in src/. It is not rendered by any route and can be deleted outright. | HIGH
app/utils/validators.py lines 10, 17, 25 | DEAD | Three validator functions are defined and never called from any module. Their existence implies validation that is not happening. | MEDIUM
app/middleware/auth_middleware.py line 47 | DEAD | get_current_authenticated_user is defined and never invoked. The current_user object is rebuilt inline instead. | MEDIUM
AuditLog model + audit decorator | ORPHANED | The model and the decorator that would populate it both exist, but no route calls the decorator. The audit table is created and permanently empty. | HIGH
SiteSettings / ContactInfo models | ORPHANED | Both tables are created by the migration and never read or written by any route. The website has no server-side settings. | HIGH
PageContent model | ORPHANED | Modelled with slug, title and body, then never exposed. No FAQ or CMS content can be managed. | HIGH
frontend invoiceService.ts + invoiceEmailService.ts | ORPHANED | Both are fully written localStorage fakes for a backend feature that does not exist. The most misleading files in the repository. | CRITICAL
src/data/*.ts seed files | DEAD | Five files of hardcoded product, category, content and navigation data shadow real database entities and are the reason the frontend appears to work. | HIGH
flasgger Swagger configuration | DEAD | Swagger is configured in create_app but the package is not installed, so the configuration never executes and no API documentation is served. | MEDIUM
Flask-Migrate / Alembic wiring | DEAD | flask_migrate is not installed and there is no alembic.ini, so the excellent 369-line migration cannot be applied by any documented command. | CRITICAL
models/product.py calculate_final_price | DEAD | Duplicated from product_service.py:16. One of the two copies is unreachable, and they can drift apart silently. | MEDIUM
Notification service callers | ORPHANED | Callers invoke notify_order_confirmation() believing an email was sent. It only writes a log line. | CRITICAL
src/components/admin/ImageUploadField.tsx | ORPHANED | Stores base64 in localStorage instead of calling the upload route that already exists in the backend. Real infrastructure sits unused. | HIGH
Festivab admin CRUD | MISSING | festival_service exists and is called only for reads. No admin write path exists, so festival promotions are configured by hand in SQL. | HIGH

## Duplicates
Duplicate and redundant implementations
The same concept implemented twice — once correctly in the backend and once as localStorage fiction in the frontend. This duplication is the structural cause of the 0% integration score.
Concept | Implemented in | Consequence of the duplication | Severity
Products | backend product_service.py vs src/data/products.ts | A working product API and a hardcoded product array. The frontend array is always newer in appearance and always stale in truth. | CRITICAL
Categories | backend products.py category routes vs src/data/categories.ts | Category management is genuinely complete at 100% on the backend, and completely bypassed on the frontend. | HIGH
Coupons | backend coupon_service.py vs src/services/couponService.ts | A correct discount engine with usage limits and expiry, shadowed by a localStorage stub. | HIGH
Authentication | backend auth_service.py JWT vs adminAuthService.ts demo tokens | Real bcrypt and real JWT issuance on one side; DEMO_PASSWORD='demo123' and demo-token-<id> on the other. | CRITICAL
Invoices | invoiceService.ts vs nothing | A complete-looking invoice generator in the browser for a backend model that was never written. | CRITICAL
Email | invoiceEmailService.ts vs nothing | A service named 'sendInvoiceEmail' that sends no email. | CRITICAL
Orders | backend order_service.py vs src/services/orderService.ts | A correct order lifecycle with row locking and history, replaced by a localStorage append. | CRITICAL
Site settings | SiteSettings model vs settingsService.ts | A database table that is always empty, and a browser object that always 'works'. | HIGH
Page content | PageContent model vs src/data/content.ts | A CMS model with no route, shadowed by a hardcoded content file. | MEDIUM
calculate_final_price | product_service.py:16 vs models/product.py:40 | The same pricing rule written twice. The two copies will drift; the model copy is unreachable. | MEDIUM
CORS allowlist | config.py lines 43-44 | The allowed-origins list is defined twice in the same file, so an edit to one is silently ignored. | MEDIUM
Seed credentials | seed_db.py vs docs | Admin@Vedhic2026 and Customer@123 hardcoded in code and repeated in documentation. | HIGH
Festival data | festival_service.py vs frontend content data | Server-side festival logic exists and is never consulted by the frontend, which uses static content data. | MEDIUM

## Database Audit
Database Audit — schema, migrations, integrity
The schema is the strongest asset in this repository. 15 tables, a real Alembic baseline, proper constraints. The problems are in what the application never writes to them.
TABLES MODELLED |  | MIGRATION LINES |  | TABLES NEVER WRITTEN | DATA INTEGRITY GAPS | DB SCORE
15 |  | 369 |  | 4 | 6 | 82%
MODELLED ENTITIES
Entity | Status | Columns of note | Finding | Severity
User | REAL | id, email (unique), password_hash, role, first/last name, phone, is_active, is_verified, timestamps. | Auth and ownership anchor. is_verified exists but no route ever sets it. | LOW
Address | REAL | User FK, label, full address, city, state, pincode, is_default, type (shipping/billing). | Proper default-address handling and a CHECK on the address type enum. | LOW
Category | REAL | name, slug (unique), description, image_url, is_active, display_order, timestamps. | Indexed slug, ordered, visibility-controlled. The most complete entity. | LOW
Product | REAL | SKU (unique), category FK, name, slug (unique), description, base_price, sale_price, stock_quantity, images JSON, is_active, is_featured, rating cache, timestamps. | CHECK constraint keeps sale_price below base_price. Soft delete via is_active is inconsistent with ProductCategory. | MEDIUM
ProductCategory | REAL | Many-to-many association between Product and Category with a composite primary key. | No soft-delete column, so deleting a product leaves orphaned join rows. | MEDIUM
Order | REAL | order_number (unique), User FK, status enum, subtotal, discount, shipping, tax, total, coupon code, address snapshot JSON, placed_at, timestamps. | Address is snapshotted correctly so later address edits do not corrupt history. | LOW
OrderItem | REAL | Order FK, Product FK, product name and price snapshots, quantity, line_total. | Correctly denormalised so historical orders survive product edits or deletion. | LOW
OrderStatusHistory | REAL | Order FK, from_status, to_status, changed_by FK, note, created_at. | Excellent audit trail. Written on every transition by order_service. | LOW
Payment | REAL | Order FK (unique), razorpay_order_id (unique), razorpay_payment_id (unique), signature, amount, status enum, method, captured_at, refunded_at, raw payload JSON. | Three unique constraints prevent duplicate captures. The unique Order FK is correct — one payment per order. | LOW
Coupon | REAL | code (unique), type enum, value, min_order_value, max_discount, usage_limit, used_count, per_user_limit, starts_at, expires_at, is_active. | The most thoroughly constrained table. Validation is shared with coupon_service. | LOW
Review | REAL | User FK, Product FK, rating 1-5, title, body, is_approved, timestamps. | CHECK on the rating range. No verified-purchase flag and no moderation workflow. | MEDIUM
FestivalBlock | REAL | name, description, starts_at, ends_at, is_active, banner_image, theme JSON. | Correct date semantics, but no admin write route and no scheduled expiry. | MEDIUM
PageContent | ORPHANED | slug (unique), page_key, title, body, meta JSON, is_published, timestamps. | A complete CMS model with zero routes attached. Permanently empty. | HIGH
AuditLog | ORPHANED | User FK, action, entity_type, entity_id, old/new values JSON, ip_address, user_agent, created_at. | Fully defined and indexed, and the decorator to populate it exists. No call site ever invokes it. | HIGH
SiteSettings / ContactInfo | ORPHANED | Key/value website settings; contact email, phone, address, social links. | Created by the migration, never read or written. The website has no server-side settings at all. | HIGH
MIGRATION QUALITY
Aspect | Status | Detail |  | Severity
Alembic baseline | REAL | One revision, b5016aa543f4_initial_schema.py, 369 lines, creates all 15 tables in dependency order with server defaults and timestamps. |  | LOW
Indexes | REAL | Index on every foreign key, on unique business columns (slug, sku, order_number, coupon code) and on status columns used for filtering. |  | LOW
Foreign keys | REAL | ON DELETE CASCADE applied where appropriate, RESTRICT or no-action where history must be preserved. This is deliberate and correct. |  | LOW
CHECK constraints | REAL | Status enums and the rating range are enforced at the database level, not only in Python. This is the mark of a careful schema. |  | LOW
alembic.ini | MISSING | The versions directory exists but alembic.ini does not, so flask db upgrade cannot be run as the README implies. |  | HIGH
migrations/env.py | PARTIAL | Falls back to a hardcoded database URL instead of requiring DATABASE_URL from the environment. |  | MEDIUM
Migration safety | PARTIAL | A single squashed baseline is fine at this stage, but there is no production data to preserve, so a second revision adding audit indexes will be needed. |  | MEDIUM
DATA INTEGRITY GAPS
Gap | Severity | Impact | Fix | Phase
AuditLog never written | HIGH | The audit trail is empty. There is no record of who changed a price, an order status or a role. | Invoke the existing audit decorator on every mutating admin route. | Phase 7
SiteSettings / ContactInfo never written | HIGH | The website's configuration lives only in one developer's browser. | Add GET/PUT admin settings routes and a settingsService that calls them. | Phase 7
PageContent never written | HIGH | No FAQ or CMS page can be created without direct SQL access. | Add admin CRUD routes and publish the slug to the frontend. | Phase 7
Wishlist has no unique constraint | MEDIUM | Without UNIQUE(user_id, product_id) a user can add the same product repeatedly and the wishlist count is wrong. | Add a composite unique constraint in a new migration. | Phase 3
Inconsistent soft delete | MEDIUM | Product uses is_active while ProductCategory has no equivalent, so deactivating a product leaves join rows and filters disagree. | Choose one strategy and apply it to both tables. | Phase 3
Decimal vs float for money | MEDIUM | If any price column is a Float rather than Numeric, repeated arithmetic will drift. Verify all money columns are Numeric(12,2). | Audit all money columns; convert any Float to Numeric. | Phase 1
Payment status not constrained to Order status | LOW | A Payment can reach 'captured' while its Order still says 'pending' if a webhook is missed and nothing reconciles. | Add a reconciliation job and a periodic consistency check. | Phase 5

## Authentication Audit
Authentication Audit
The cryptography is right. The configuration and the verification workflow are not. This sheet is the reason auth scores 57% rather than 90%.
AUTH SCORE |  | CRITICAL FINDINGS |  | HIGH FINDINGS | PASSWORD POLICY | EMAIL VERIFICATION
57% |  | 2 |  | 3 | STRONG | ABSENT
Aspect | Status | Finding | Location | Severity
Password hashing | REAL | bcrypt via flask_bcrypt with an appropriate work factor. Hashing is done in auth_service, not in the route. | app/services/auth_service.py | LOW
Password policy | REAL | A minimum length, upper, lower, digit and special-character policy, implemented as a pure function so it is directly testable. | app/services/auth_service.py | LOW
JWT issuance | PARTIAL | Access and refresh tokens are issued with expiry and a token version for revocation, but flask_jwt_extended is not in requirements.txt so this cannot run. | app/routes/auth.py | CRITICAL
JWT secret configuration | BROKEN | config.py lines 11-12 hardcode fallback SECRET_KEY and JWT_SECRET_KEY values. A missing .env silently produces a publicly known signing key instead of failing loudly. | backend/config.py:11 | CRITICAL
DEV_SECRET fallback | BROKEN | auth_middleware.py will substitute a development secret when the configured key is absent, which means a misconfigured production deploy signs tokens everyone can forge. | app/middleware/auth_middleware.py | CRITICAL
Token revocation | PARTIAL | A token_version column supports invalidation, but there is no logout blacklist and no refresh-token rotation with reuse detection. | app/services/auth_service.py | HIGH
Email verification | MISSING | User.is_verified exists in the schema and is never set. Anyone can register and immediately act as a verified account. | app/routes/auth.py | HIGH
Forgot password | BROKEN | The endpoint exists and returns a fake generic success message, but there is no mail provider, so no reset email is ever sent. Users are permanently locked out. | app/routes/auth.py | CRITICAL
Reset password | BROKEN | The consuming endpoint exists, but nothing can ever reach it because the email is never sent. The flow is decorative. | app/routes/auth.py | CRITICAL
Rate limiting on login | PARTIAL | rate_limiter.py exists, but it is an in-process dictionary: it resets on every deploy, is not shared across workers and is unbounded in memory. | app/middleware/rate_limiter.py | HIGH
Account lockout | MISSING | No failed-attempt counter and no lockout, so credential stuffing against a known email is unthrottled in practice. | Absent | MEDIUM
Duplicate email handling | REAL | Uniqueness is enforced by the database and checked in the service before insert, returning a proper conflict response. | app/services/auth_service.py | LOW
Frontend authentication | MOCK | adminAuthService.ts hardcodes DEMO_PASSWORD='demo123' and issues demo-token-<id> strings. The admin panel's 'login' proves nothing about the backend. | src/services/adminAuthService.ts:33 | CRITICAL
Session authority | MISSING | adminStore.ts persists an admin session entirely in localStorage. A user can set isAdmin locally and the UI will render admin screens. There is no server-side authority. | src/services/adminStore.ts | CRITICAL
Seed credentials | PARTIAL | seed_db.py hardcodes Admin@Vedhic2026 and Customer@123 and is safe to run against production by accident. | backend/seed_db.py | HIGH

## RBAC Audit
Authorization & RBAC Audit
There is no role-based access control. There is one boolean and a string comparison. This is the lowest-scoring area of the backend at 11%.
RBAC SCORE |  | DISTINCT ROLES |  | PERMISSIONS DEFINED | STAFF ACCOUNTS | OWNERSHIP CHECKS
11% |  | 2 |  | 0 | 0 | 2 of 57
WHAT EXISTS
Mechanism | Status | Detail | Location | Severity
User.role column | PARTIAL | A single VARCHAR with exactly two values used anywhere in the codebase: 'USER' and 'ADMIN'. There is no lookup table, no enum and no validation of allowed values. | app/models/user.py | HIGH
admin_required decorator | PARTIAL | The decorator exists and is applied to admin routes, but its entire authorization logic on line 35 is role != 'ADMIN'. | app/middleware/auth_middleware.py:35 | CRITICAL
login_required decorator | REAL | Correctly validates the JWT and attaches the identity. This is the one part of the auth stack that works as intended. | app/middleware/auth_middleware.py | LOW
Ownership scoping | PARTIAL | Orders, cart, addresses and wishlist do filter by user_id. This is genuine and worth keeping. It is simply not applied consistently elsewhere. | app/routes/orders.py | MEDIUM
WHAT IS MISSING
Missing capability | Severity | Consequence | Where it should live | Phase
Role hierarchy | CRITICAL | There is no way to distinguish a store manager from a support agent from a super admin. Everyone with ADMIN can change prices and issue refunds. | app/models/role.py | Phase 2
Permission matrix | CRITICAL | No granular permissions exist, so access is all-or-nothing. A newly hired staff member is either fully trusted or has no access at all. | app/middleware/rbac.py | Phase 2
Resource ownership enforcement | CRITICAL | /api/payments/verify and /api/payments/<id> never receive user_id, so a caller who guesses an order_id can read or confirm another customer's payment. | app/routes/payments.py:81 | Phase 5
Staff management | CRITICAL | No staff model, no invite flow, no deactivation, no activity attribution. Shared admin credentials are the only option, which is untraceable and unsafe. | app/routes/admin.py | Phase 2
Audit trail population | HIGH | AuditLog and its decorator exist but no mutating route invokes the decorator, so privileged actions leave no record. | app/models/audit_log.py | Phase 7
Field-level restrictions | MEDIUM | No mechanism prevents a staff member from editing price, cost or role fields while still editing a product. | app/schemas/product.py | Phase 2
Route-level permission map | MEDIUM | No declarative mapping of route to required permission, so reviewing authorization means reading every decorator by hand. | app/middleware/rbac.py | Phase 2
Frontend route guards | HIGH | Admin screens are guarded only by a localStorage flag, so a user can navigate to /admin directly and the UI will render. | src/pages/admin | Phase 10
Self-privilege escalation guard | HIGH | No check prevents a user from editing their own role or another admin's account. | app/routes/admin.py | Phase 2

## Product & Image Audit
Product, Image Upload & Inventory Audit
Product CRUD is genuinely good. Image upload has real infrastructure that is bypassed by the frontend, and inventory is a single integer with no ledger behind it.
PRODUCTS |  | CATEGORIES |  | IMAGE UPLOAD | INVENTORY | BLOCKING DEFECTS
70% |  | 100% |  | 73% | 50% | 3
PRODUCTS
Aspect | Status | Finding | Location | Severity
Product CRUD | REAL | Full create, read, update, delete with marshmallow validation and a unique SKU constraint. | app/routes/products.py | LOW
Categories | REAL | Complete CRUD with image, ordering, visibility and product-count rollups. 100% — nothing meaningful is missing. | app/routes/products.py | LOW
Search & filter | REAL | Text search plus filtering by category, price range, availability and featured status, with correct pagination and sort whitelist. | app/services/product_service.py | LOW
Festival pricing | REAL | calculate_final_price applies festival and sale pricing correctly. | app/services/product_service.py:16 | LOW
calculate_final_price duplication | PARTIAL | The identical rule is written again in models/product.py:40. One copy is unreachable and the two will drift apart. | app/models/product.py:40 | MEDIUM
'bestsellers' sort | BROKEN | Line 199 orders by created_at, so 'bestsellers' actually returns newest products. This is a visibly wrong feature in a storefront. | app/services/product_service.py:199 | HIGH
Soft delete | PARTIAL | Product uses is_active while ProductCategory has no equivalent column, so joins and filters disagree after a deactivation. | app/models/product.py | MEDIUM
IMAGE UPLOAD
Aspect | Status | Finding | Location | Severity
S3 service | REAL | Genuine boto3 upload with a local-filesystem fallback when S3 is unconfigured. This is real infrastructure and it works. | app/services/s3_service.py | LOW
Size limit | REAL | MAX_CONTENT_LENGTH of 5MB is set in config.py and enforced by Flask. | backend/config.py:41 | LOW
MIME validation | BROKEN | The allowlist trusts the client-supplied Content-Type header. A .php or .svg payload renamed to .jpg is accepted, and there is no magic-byte sniffing. | app/utils/validators.py:57 | HIGH
Extension allowlist | PARTIAL | An extension check exists but is redundant with the broken MIME check and gives a false sense of protection. | app/utils/validators.py | MEDIUM
Image resizing | MISSING | No Pillow dependency, so originals are stored at full resolution. A 12MP phone photo will be served as a product thumbnail. | Absent | MEDIUM
Frontend uploader | BROKEN | ImageUploadField.tsx line 28 uses FileReader.readAsDataURL and writes base64 into localStorage. It never calls the upload route that already exists, and localStorage exhausts at about 5MB. | src/components/admin/ImageUploadField.tsx:28 | CRITICAL
INVENTORY
Aspect | Status | Finding | Location | Severity
stock_quantity column | REAL | Present, non-nullable with a server default, and correctly decremented under a row lock during order placement. | app/models/product.py | LOW
Row locking | REAL | SELECT ... FOR UPDATE during reservation prevents overselling under concurrent checkouts. This is the correct pattern. | app/services/order_service.py:55 | LOW
Stock release on cancel | REAL | Cancellation returns the reserved quantity. Correctly implemented. | app/services/order_service.py | LOW
Stock ledger | MISSING | No movement history, so 'why is this number 7' cannot be answered. Every adjustment overwrites the previous value. | Absent | HIGH
Low-stock alerts | MISSING | No threshold and no notification, so a best-selling product reaches zero with no warning. | Absent | MEDIUM
Back-in-stock notification | MISSING | No subscriber model and no notification path. | Absent | MEDIUM
Manual adjustment with reason | MISSING | No admin route can adjust stock, and no reason or actor is recorded when it can. | Absent | MEDIUM
Multi-warehouse stock | MISSING | Out of scope for this project, recorded for completeness only. | Absent | LOW

## Order Audit
Order & Cart Audit
Orders score 93% — the best area in the project. The single deduction is that refunds never reach the payment gateway. This sheet explains why the implementation is worth trusting.
ORDERS |  | CART |  | REFUND | CONCURRENCY SAFETY | DEFECTS
93% |  | 95% |  | 20% | CORRECT | 2
Aspect | Status | Finding | Location | Severity
Cart operations | REAL | Add, update quantity, remove, clear and merge-on-login. The merge correctly consolidates a guest cart into the user's cart after authentication. | app/routes/cart.py | LOW
Order creation | REAL | Validates stock, computes subtotal, discount, shipping and tax server-side, snapshots the shipping address, and creates OrderItems with price snapshots. | app/services/order_service.py | LOW
Price snapshots | REAL | OrderItem stores the product name and unit price at purchase time, so historical orders survive later product edits or deletion. This is correct and often missed. | app/models/order_item.py | LOW
Stock reservation | REAL | SELECT ... FOR UPDATE on line 55 prevents two concurrent checkouts from claiming the same stock. This is the correct concurrency pattern. | app/services/order_service.py:55 | LOW
Order number | REAL | A unique human-readable order number with a database unique constraint, so collisions are impossible. | app/models/order.py | LOW
Status transitions | REAL | Transitions are validated against an allowed set and every one writes an OrderStatusHistory row with actor and note. | app/services/order_service.py | LOW
Cancellation | REAL | Validates the order is still cancellable and returns the reserved stock to inventory. | app/services/order_service.py | LOW
Order list & detail | REAL | Paginated list and detail, correctly scoped to the owning user. | app/routes/orders.py | LOW
Address snapshot | REAL | The full address is denormalised onto the order, so a later change to the user's address does not rewrite history. | app/models/order.py | LOW
Invoice endpoint | BROKEN | The invoice endpoint in orders.py is a stub returning a JSON literal. It advertises a feature that does not exist. | app/routes/orders.py | HIGH
Refund | BROKEN | Only the status string is set to 'refunded'. The Razorpay refund API is never called, so no money is ever returned to the customer. | app/services/order_service.py:196 | CRITICAL
Partial refunds | MISSING | No quantity-level or amount-level refund. A full order must be refunded to return one missing item. | Absent | MEDIUM
Order confirmation email | MISSING | notification_service is a logging stub, so a customer receives nothing after ordering. | app/services/notification_service.py | CRITICAL
Guest checkout | MISSING | Cart is available to guests but order creation requires an account, so there is no guest-to-account conversion flow. | Absent | MEDIUM
Order tracking for customers | MISSING | No shipment entity and no tracking endpoint. A customer can see a status but never a location or an ETA. | Absent | HIGH

## Payment Audit
Payment Audit — the highest-risk area in the repository
Three critical defects, one of which is the default production code path. Nothing in this sheet should be considered done until every CRITICAL row is closed.
PAYMENTS |  | RAZORPAY INTEGRATION |  | PAYMENT VERIFICATION | WEBHOOKS | CRITICAL DEFECTS
75% |  | 80% |  | 40% | 0% | 3
CRITICAL — fix before accepting any real payment
Defect | Status | Detail | Location | Severity
Signature bypass is the default path | BROKEN | Line 155: verification is skipped whenever the signature is in a hardcoded list OR simply starts with 'sig_'. Because backend/.env ships RAZORPAY_KEY_SECRET empty, the bypass is what runs in production. An attacker confirms any order with a nine-character string. | app/services/payment_service.py:155 | CRITICAL
IDOR on payment verification | BROKEN | GET and POST /api/payments/verify never receive a user_id, and verify_payment loads the Order with db.session.get(Order, order_id) with no ownership filter. Any authenticated caller who guesses or enumerates an order_id can mark another customer's order paid. | app/routes/payments.py:81 | CRITICAL
GET /api/payments/<id> returns HTTP 500 | BROKEN | The handler calls db.session.get(Payment, payment_id) but 'from app.extensions import db' was never imported into the module. Every request raises NameError and is swallowed into a generic 500. | app/routes/payments.py:100 | CRITICAL
HIGH
Aspect | Status | Finding | Location | Severity
Missing razorpay dependency | BROKEN | razorpay is not in requirements.txt, so no Razorpay code path can execute at all. | backend/requirements.txt | HIGH
Empty API keys in .env | PARTIAL | RAZORPAY_KEY_ID and RAZORPAY_KEY_SECRET are both blank. The config layer should refuse to start rather than falling through to an unsafe path. | backend/.env | CRITICAL
A test protects the bypass | BROKEN | test_payments.py sends razorpay_signature='sig_valid_hash' and asserts HTTP 200. CI currently enforces the vulnerability; fixing the service will correctly break this test. | tests/test_payments.py:63 | HIGH
Unsigned webhooks | BROKEN | The webhook handler accepts payloads with no signature verification and no event deduplication, so anyone who learns the URL can mark orders paid. | app/routes/webhooks.py | HIGH
Refund never calls the gateway | BROKEN | order_service.py sets status='refunded' and stops. The Razorpay refund API is never invoked, so the customer's money is never returned. | app/services/order_service.py:196 | CRITICAL
GENUINELY WELL BUILT — keep this
Aspect | Status | Finding | Location | Severity
Paise conversion | REAL | Correctly converts rupees to paise as integers and formats the amount string for Razorpay. No float arithmetic on money. | app/services/payment_service.py:33 | LOW
HMAC implementation | REAL | Line 144 contains a correct HMAC-SHA256 signature check. It is simply never reached because line 155 short-circuits it. Deleting the bypass is the whole fix. | app/services/payment_service.py:144 | LOW
Idempotency | REAL | Payment verification checks for an existing successful payment before acting, so a duplicate webhook or a double-submit cannot double-credit an order. | app/services/payment_service.py:109 | LOW
Razorpay order creation | REAL | Server-side order creation with amount, currency and receipt correctly assembled. | app/routes/payments.py | LOW
Payment model constraints | REAL | Unique constraints on razorpay_order_id, razorpay_payment_id and Order FK. Duplicate captures are impossible at the database level. | app/models/payment.py | LOW
Raw payload retention | REAL | The full webhook payload is stored as JSON, which is correct for dispute investigation — provided the signature is verified first. | app/models/payment.py | LOW
FRONTEND PAYMENT PATH
Aspect | Status | Finding | Location | Severity
PaymentGateway.tsx | BROKEN | Line 48 uses Math.random() < 0.15 to randomly simulate a payment failure. This is a coin flip presented to the customer as a gateway response. | src/components/checkout/PaymentGateway.tsx:48 | CRITICAL
Honest source comment | REAL | Line 131 of the same file states plainly that no real money moves. Worth crediting — the code is not pretending to be more than it is. | src/components/checkout/PaymentGateway.tsx:131 | LOW
No gateway script loaded | MISSING | Razorpay Checkout is never loaded and no order_id is ever obtained, so there is nothing to open. | src/components/checkout | CRITICAL

## Invoice & Email
Invoice, PDF & Email Audit
Three capabilities at 0%. The frontend already has convincing localStorage implementations of both, which is why this absence is easy to miss in a demo.
INVOICES |  | INVOICE PDF |  | INVOICE EMAIL | MAIL DEPENDENCIES | FRONTEND FAKES
0% |  | 0% |  | 0% | 0 | 2
Capability | Status | Finding | Location | Severity
Invoice model | MISSING | No Invoice table, no invoice_number, no issue_date, no due_date, no line-item snapshot, no tax breakdown. Nothing exists to store an invoice. | Absent | CRITICAL
Invoice schema | MISSING | No marshmallow schema. The other 12 entities all have one, so the absence here is conspicuous. | app/schemas | CRITICAL
Invoice routes | MISSING | No endpoint to list, fetch, download or void an invoice. The stub in orders.py returns a JSON literal and is not an invoice. | app/routes | CRITICAL
PDF generation | MISSING | No PDF library in requirements.txt (no reportlab, weasyprint, fpdf2 or pdfkit), no template directory, no renderer and no download endpoint. | Absent | CRITICAL
Invoice numbering | MISSING | No sequential financial numbering scheme, which is an accounting requirement in India for GST invoices. | Absent | HIGH
GST / tax breakdown | MISSING | Orders store a single tax_total. There is no CGST/SGST split, no HSN code and no tax rate snapshot per line, all of which Indian GST invoices require. | Absent | HIGH
Transactional email | MISSING | No SMTP client, no SES, no SendGrid, no Resend. requirements.txt contains no mail library of any kind. | backend/requirements.txt | CRITICAL
Email templates | MISSING | No templates directory, no Jinja mailer, no branded HTML and no plain-text alternative. | Absent | HIGH
Email queueing | MISSING | No Celery and no Redis, so there is no way to send mail asynchronously or retry a failed send. | Absent | HIGH
Order confirmation email | MISSING | notification_service.py is a logging stub. Callers believe the customer has been notified when nothing was sent. | app/services/notification_service.py | CRITICAL
Password reset email | MISSING | The forgot-password endpoint returns a fake success message with no email behind it, so locked-out users are never rescued. | app/routes/auth.py | CRITICAL
Email verification | MISSING | No verification email, so is_verified stays false forever and accounts are never confirmed. | app/routes/auth.py | HIGH
Frontend invoiceService.ts | BROKEN | A complete-looking invoice generator writing to localStorage for a backend that has no invoice feature. The most misleading file pair in the project. | src/services/invoiceService.ts | CRITICAL
Frontend invoiceEmailService.ts | BROKEN | A function named 'sendInvoiceEmail' that sends no email and writes a log entry to localStorage. | src/services/invoiceEmailService.ts | CRITICAL
Delivery tracking email | MISSING | No shipment entity and no tracking notification. | Absent | MEDIUM

## Admin Settings
Admin, Settings & Content Audit
The backend models for settings and content exist and are never used. The frontend has local versions of both. Website configuration currently lives in one developer's browser.
ADMIN ENDPOINTS |  | WEBSITE SETTINGS |  | CONTACT SETTINGS | FAQ / CONTENT | ORPHANED MODELS
17 |  | 0% |  | 0% | 0% | 3
PRESENT IN admin.py
Area | Status | Finding | Location | Severity
Product management | REAL | Full admin CRUD, bulk operations and image handling. Genuinely complete. | app/routes/admin.py | LOW
Order management | REAL | List, filter, update status with history, and cancellation. Correct and complete. | app/routes/admin.py | LOW
Coupon management | REAL | Create, edit, deactivate and inspect usage. Backed by the real coupon_service. | app/routes/admin.py | LOW
Customer listing | REAL | Paginated customer list with order counts. No customer detail view and no notes. | app/routes/admin.py | MEDIUM
Dashboard analytics | PARTIAL | Revenue, order-count and top-product aggregates computed in Python. No date range, no comparison, no caching, and no timezone handling. | app/routes/admin.py | MEDIUM
ABSENT FROM admin.py — all scored 0%
Missing admin area | Severity | Why the product needs it | Backend asset available | Phase
Staff & role management | CRITICAL | No way to onboard a teammate, revoke access or attribute an action to a person. Shared credentials are the only option. | None — must be built | Phase 2
Invoice management | CRITICAL | No invoice list, search, void, regenerate or download. A completed sale has no financial record. | None — must be built | Phase 6
Settings management | HIGH | Site name, logo, contact details, social links and policies cannot be changed without a database console. | SiteSettings and ContactInfo models already exist | Phase 7
Content & FAQ management | HIGH | FAQ, about, terms and privacy pages cannot be edited by anyone. | PageContent model already exists | Phase 7
Inventory management | HIGH | No stock list, no low-stock view, no adjustment with a reason, no movement history. | stock_quantity column exists | Phase 3
Delivery & tracking | HIGH | No way to tell a customer where an order is or when it will arrive. | None — must be built | Phase 3
Audit log viewer | HIGH | The AuditLog table exists but nothing writes to it and no screen displays it. | AuditLog model and decorator exist | Phase 7
Review moderation | MEDIUM | Reviews can be created but never approved, rejected or featured from the admin. | reviews.py has no admin routes | Phase 7
Festival promotion management | HIGH | Festival blocks can only be read, never created or edited, so promotions are configured by hand in SQL. | festival_service has the logic | Phase 3
Support inbox | MEDIUM | No ticket or conversation model, so customer messages have no destination. | None — must be built | Phase 7
Refund management | CRITICAL | No admin action to issue a refund, and the service layer never calls the gateway API even when triggered. | Order status transition exists | Phase 5
Coupon usage analytics | LOW | No redemption rate or revenue impact reporting. | Coupon.used_count is tracked | Phase 7

## Security Audit
Security Audit — 19 findings
Six critical, five high, five medium, three low. Four of the six critical findings are configuration or authorization defects rather than exotic vulnerabilities, which is good news: they are all straightforward to close.
CRITICAL |  | HIGH |  | MEDIUM | LOW | SECURITY SCORE
6 |  | 5 |  | 5 | 3 | 53%
FINDINGS
# | Finding | Severity | Detail | Location
1 | Payment signature bypass in the default path | CRITICAL | verify_payment accepts any signature starting with 'sig_' when RAZORPAY_KEY_SECRET is empty, and backend/.env ships it empty. Any party can mark any order as paid. | app/services/payment_service.py:155
2 | IDOR on /api/payments/verify | CRITICAL | The endpoint receives no user_id and the Order is loaded with no owner filter, so a caller can confirm or read another customer's payment by guessing an order_id. | app/routes/payments.py:81
3 | Hardcoded fallback secrets | CRITICAL | config.py lines 11-12 hardcode SECRET_KEY and JWT_SECRET_KEY, and auth_middleware substitutes a DEV_SECRET when the real key is absent. A misconfigured deploy signs tokens anyone can forge. | backend/config.py:11-12
4 | Debug server bound to all interfaces | CRITICAL | run.py forces DevelopmentConfig and debug=True on 0.0.0.0, exposing the interactive Werkzeug debugger, which permits remote code execution. | backend/run.py:5-9
5 | Unsigned webhook endpoint | CRITICAL | The webhook handler performs no signature verification and has no event deduplication, so anyone who learns the URL can credit orders. | app/routes/webhooks.py
6 | Refunds never reach the gateway | CRITICAL | The refund path only writes a status string. The Razorpay refund API is never called, so a customer is told they were refunded while keeping their money. | app/services/order_service.py:196
7 | Broken admin authentication in the frontend | HIGH | DEMO_PASSWORD='demo123' and demo-token-<id> strings, with the admin session held entirely in localStorage. Any user can grant themselves admin in the browser. | src/services/adminAuthService.ts:33
8 | No RBAC — binary role check | HIGH | Authorization is role != 'ADMIN' with no permission model, no staff roles and no field-level restrictions. | app/middleware/auth_middleware.py:35
9 | Upload validation trusts the client | HIGH | The MIME allowlist reads the client-supplied Content-Type header with no magic-byte sniffing, so a disguised executable is accepted. | app/utils/validators.py:57
10 | In-process rate limiter | HIGH | A dictionary in memory resets on every deploy, is not shared across workers and grows without bound, so brute-force protection is effectively absent in production. | app/middleware/rate_limiter.py
11 | Audit trail never written | HIGH | AuditLog and its decorator exist but no mutating route calls it, so privileged actions leave no record. | app/models/audit_log.py
12 | No account lockout | MEDIUM | No failed-attempt counter or lockout on login, so credential stuffing against a known email is unthrottled. | app/routes/auth.py
13 | No security headers beyond the basics | MEDIUM | Content-Security-Policy, Strict-Transport-Security, Referrer-Policy and Permissions-Policy are all absent. | app/__init__.py
14 | CORS allowlist duplicated | MEDIUM | The allowed-origins list appears twice in config.py, so an edit to one copy is silently ignored — a classic source of a too-permissive origin surviving review. | backend/config.py:43-44
15 | Secrets in plaintext on developer disks | MEDIUM | Correctly git-ignored, and git ls-files confirms backend/.env is untracked. The residual issue is only that live secrets sit unencrypted on disk. Downgraded from the earlier HIGH claim. | backend/.env
16 | No dependency pinning for production | MEDIUM | requirements.txt omits eight required packages entirely and requirements-dev.txt disagrees with it, so builds are not reproducible. | backend/requirements.txt
17 | Health check does not verify the database | LOW | /health returns a static dict, so an orchestrator reports healthy while the application is completely non-functional. | app/routes/health.py
18 | Error responses may leak internals | LOW | Verify that the 500 handler does not serialize the exception message or a SQLAlchemy statement back to the client. | app/middleware/error_handler.py
19 | No CSRF consideration for cookie-based flows | LOW | Currently moot because auth is bearer-token based. Revisit if tokens are ever moved to httpOnly cookies. | N/A
HARDENING ROADMAP
Order | Action | Severity | Effort | Phase
1 | Delete the payment signature bypass and fail closed when the secret is empty | CRITICAL | 1 hour | Phase 5
2 | Thread user_id through /verify and enforce order ownership | CRITICAL | 2 hours | Phase 5
3 | Remove the hardcoded fallback secrets; raise on missing config in production | CRITICAL | 1 hour | Phase 1
4 | Replace run.py with a gunicorn entrypoint and debug=False always | CRITICAL | 1 hour | Phase 10
5 | Verify webhook signatures and add an event deduplication table | CRITICAL | 4 hours | Phase 5
6 | Call the Razorpay refund API and reconcile against the gateway | CRITICAL | 4 hours | Phase 5
7 | Implement RBAC with roles, permissions and field-level rules | HIGH | 3 days | Phase 2
8 | Add magic-byte image validation and a shared Redis rate limiter | HIGH | 1 day | Phase 8
9 | Populate AuditLog from every mutating admin route | HIGH | 1 day | Phase 7
10 | Add CSP, HSTS, Referrer-Policy and Permissions-Policy headers | MEDIUM | 2 hours | Phase 8

## API Audit
API Surface Audit
The HTTP layer is consistent and well organised. The weaknesses are operational: no versioning, no rate-limit headers, no published schema and no consumer.
ENDPOINTS |  | BLUEPRINTS |  | SCHEMAS | API SCORE | FRONTEND CONSUMERS
~57 |  | 13 |  | 12 | 80% | 0
BLUEPRINT INVENTORY
Blueprint | Status | Assessment | Notable issue | Severity
auth | PARTIAL | register, login, refresh, logout, me, forgot-password, reset-password. Two of the seven are non-functional without email. | forgot/reset password return fake success | CRITICAL
products | REAL | Product and category CRUD, search, filter, sort, pagination. The strongest blueprint in the project. | None | LOW
cart | REAL | Add, update, remove, clear, merge-on-login. Complete and correct. | None | LOW
orders | PARTIAL | Create, list, detail, status update, cancel, invoice stub. | The invoice endpoint is a stub returning a literal | HIGH
payments | BROKEN | Create Razorpay order, verify, status, webhook. | NameError on line 100; IDOR on line 81 | CRITICAL
coupons | REAL | Validate, apply, list, admin manage. Backed by thorough validation. | None | LOW
reviews | PARTIAL | CRUD with rating aggregation. | No moderation and no admin route | MEDIUM
admin | PARTIAL | 17 endpoints for products, orders, coupons, customers, analytics. | No staff, settings, invoices, inventory, audit or refund | HIGH
customer | PARTIAL | Profile, addresses, order history, wishlist. | No customer notes or admin detail view | MEDIUM
upload | PARTIAL | Image upload via s3_service with a local fallback. | MIME check trusts the client header | HIGH
festival | PARTIAL | Festival block reads and product association. | No admin write route at all | HIGH
webhooks | BROKEN | Razorpay event receipt. | No signature check, no deduplication, no retry | CRITICAL
health | PARTIAL | Liveness and readiness response. | Never checks the database, so it lies | HIGH
CROSS-CUTTING API GAPS
Gap | Severity | Impact | Recommendation | Phase
No versioning | MEDIUM | The URL space is /api/* with no version prefix, so a breaking change cannot be rolled out alongside the old contract. | Prefix /api/v1 and treat the current paths as v1. | Phase 10
No published schema | MEDIUM | flasgger is configured in create_app but not installed, so no OpenAPI document is served and the frontend cannot generate types. | Install flasgger and publish the spec. | Phase 1
No rate-limit headers | MEDIUM | X-RateLimit-Limit, -Remaining and -Reset are never returned, so clients cannot back off correctly. | Emit the headers from rate_limiter. | Phase 8
No idempotency on order creation | MEDIUM | A double-tapped Place Order creates two orders. Verification is idempotent but order creation is not. | Accept an Idempotency-Key on POST /api/orders. | Phase 4
No pagination metadata | LOW | Lists return bare arrays, so the client cannot render a pager without inferring page size. | Return {items, total, page, pages}. | Phase 4
No request correlation id | LOW | A client-reported failure cannot be tied to a specific log line. | Generate a UUID per request and echo it in a header. | Phase 8
Inconsistent error shape | LOW | Most routes use the error_handler envelope, but ad hoc abort() calls bypass it in places. | Route all errors through one handler. | Phase 8
No API consumer | CRITICAL | The most important gap. Nothing in the frontend calls any of these 57 endpoints, so none of this work is reachable by a customer. | Replace mockRequest() with fetch(). | Phase 10

## Testing Audit
Testing & CI Audit
21 tests across 11 files, none of which has ever been executed. The suite cannot start because TestingConfig requires a provisioned PostgreSQL instance.
TEST FILES |  | TEST FUNCTIONS |  | TESTS EXECUTED | CI WORKFLOWS | TESTING SCORE
11 |  | 21 |  | 0 | 0 | 33%
WHY THE SUITE CANNOT RUN
Blocker | Status | Detail | Location | Severity
PostgreSQL-only TestingConfig | BROKEN | TestingConfig hardcodes a PostgreSQL DSN with no SQLite fallback, so a contributor must provision a database before running a single test. | backend/config.py | HIGH
Missing test dependencies | BROKEN | pytest and pytest-cov are installed, but flask_jwt_extended, flask_bcrypt and marshmallow are not, so importing the app in conftest fails before collection. | backend/requirements.txt | CRITICAL
No CI workflow | MISSING | There is no .github directory, so nothing runs the suite on push or pull request and no regression can be caught. | Absent | HIGH
Destructive fixtures | PARTIAL | A fixture truncates tables with a hardcoded raw DELETE FROM list. Adding a table means editing that list, and forgetting to do so causes cross-test contamination. | tests/conftest.py | HIGH
Session-scoped schema | PARTIAL | create_all runs once for the whole session and there is no per-test transaction rollback, so tests can only be safely ordered by hand. | tests/conftest.py | MEDIUM
Fixed auth token fixture | PARTIAL | auth_headers returns a hardcoded token string rather than a freshly minted one, so a JWT secret change silently invalidates every authenticated test. | tests/conftest.py | MEDIUM
EXISTING TEST INVENTORY
Test file | Status | Coverage | Assessment | Severity
test_auth.py | PARTIAL | Registration, login, duplicate email, password policy, JWT shape. | Reasonable, but never executed. No refresh, logout or revocation coverage. | MEDIUM
test_products.py | PARTIAL | Product CRUD, search, filter, pagination, category CRUD. | The best-written test file. No festival pricing or sale-price edge cases. | MEDIUM
test_cart.py | PARTIAL | Add, update, remove, clear, merge-on-login. | Never executed. No concurrent-cart or negative-stock case. | MEDIUM
test_orders.py | PARTIAL | Create, list, status transition, cancellation, stock release. | Valuable coverage of the strongest service. No refund or partial-cancel case. | MEDIUM
test_payments.py | BROKEN | Razorpay order creation and signature verification. | Line 63 sends 'sig_valid_hash' and asserts 200, so CI currently enforces the signature bypass. Fixing payment_service.py:155 will correctly break this test. | CRITICAL
test_coupons.py | PARTIAL | Validation, min order, expiry, usage limits, per-user limit. | Good coverage of a genuinely complete service. | LOW
test_admin.py | PARTIAL | Admin authorisation and product/order management. | Never executed. No role-matrix coverage, because no roles exist. | MEDIUM
test_models.py | PARTIAL | Model construction and relationships. | Shallow. No constraint tests for unique indexes or CHECK conditions. | MEDIUM
test_utils.py | PARTIAL | Password policy and helper functions. | The only tests that could run without a database. | LOW
test_upload.py | PARTIAL | Upload validation. | No test for a disguised file type, which is exactly the gap the broken MIME check leaves. | HIGH
test_reviews.py | PARTIAL | Review CRUD and rating aggregation. | No moderation workflow coverage. | LOW
UNCOVERED — NO TEST EXISTS AT ALL
Uncovered area | Severity | Why it matters | Recommended first test | Phase
Payment signature rejection | CRITICAL | The most dangerous defect in the project has no negative test. A test asserting a bad signature is rejected would have caught it. | Assert 400 for a tampered signature and for an empty server secret. | Phase 5
Payment ownership (IDOR) | CRITICAL | No test verifies that user A cannot confirm user B's order. The bypass would be caught immediately. | Assert 403 when user_id does not own the order. | Phase 5
Webhook signature verification | CRITICAL | Unsigned webhooks are accepted today and no test would notice. | Assert 400 for a payload with an invalid signature. | Phase 5
Auth middleware role matrix | HIGH | No test covers non-admin access to admin routes. | Assert 403 for USER against every admin_required route. | Phase 2
Stock concurrency | HIGH | The FOR UPDATE locking is the best code in the project and is untested under contention. | Spawn concurrent checkouts and assert stock never goes negative. | Phase 3
Refund calls the gateway | CRITICAL | The refund path silently does nothing and no test asserts the API call. | Mock Razorpay and assert refund payment_id is recorded. | Phase 5
Frontend-to-backend contract | CRITICAL | There is no integration test because there is no integration. | One Playwright test: register, add to cart, pay, see the order. | Phase 10

## Roadmap
Remediation Roadmap — 10 phases
Sequenced by dependency, not by severity alone. Phases 1 and 2 are prerequisites for everything else. Total estimated effort is roughly 41 working days for one engineer.
PHASES |  | CRITICAL PHASES |  | TOTAL EFFORT |  | BLOCKS LAUNCH | CURRENT STATE
10 |  | 5 |  | ~41 days |  | Phases 1,2,5,6,10 | 0% E2E
# | Phase | Effort | Priority | Scope | Why this order
1 | Critical Backend Foundation | 1 day | CRITICAL | Install the eight missing dependencies so the app factory stops raising ModuleNotFoundError. Add alembic.ini. Remove the hardcoded secret fallbacks in config.py and raise on missing config in production. Pin requirements.txt and reconcile requirements-dev.txt. Install flasgger and publish the OpenAPI spec. Result: the backend starts and the migration can be applied. | Unblocks every later phase
2 | Authentication & RBAC | 5 days | CRITICAL | Implement the Role and Permission models with a real permission matrix. Replace the binary role check with a declarative route-to-permission map. Add staff management: invite, deactivate, attribute actions. Add field-level restrictions so a staff member cannot edit price or role. Add email verification, refresh-token rotation with reuse detection, and account lockout. Add a frontend route guard backed by the server session. | No staff can work safely before this
3 | Product, Inventory & Delivery | 4 days | HIGH | Fix the 'bestsellers' sort and remove the calculate_final_price duplication. Add a stock movement ledger with actor and reason, a low-stock threshold and a back-in-stock notification. Add admin festival CRUD. Add a Shipment and Tracking model with an admin status workflow and a customer tracking endpoint. Add the missing (user_id, product_id) unique constraint on wishlist. | Orders cannot be fulfilled
4 | Customer & Order Experience | 2 days | MEDIUM | Add an Idempotency-Key to POST /api/orders so a double tap cannot create two orders. Return pagination metadata as {items, total, page, pages}. Add guest checkout with account conversion. Add admin customer detail and internal notes. | Improves conversion and trust
5 | Razorpay & Payment Verification | 3 days | CRITICAL | Delete the signature bypass at payment_service.py:155 and fail closed when the secret is empty. Thread user_id through GET/POST /api/payments/verify and enforce order ownership. Add the missing db import to payments.py. Verify webhook signatures and add an event deduplication table. Call the real Razorpay refund API and add a reconciliation job. Rewrite test_payments.py so a bad signature is rejected. Configure real API keys. | THE phase for taking money
6 | Invoicing & Transactional Email | 4 days | CRITICAL | Create the Invoice model with sequential invoice_number, issue date, line-item and tax snapshots, and an Indian GST breakdown (CGST/SGST, HSN). Add a PDF renderer and a download endpoint. Integrate a transactional email provider with Jinja templates, a Celery/Redis queue and retry. Wire order confirmation, password reset and email verification to real sends. | A sale without a receipt is not a business
7 | Admin Settings, Content & Audit | 6 days | HIGH | Wire SiteSettings, ContactInfo and PageContent to admin CRUD routes and migrate the frontend settings to use them. Populate AuditLog from every mutating admin route and build an audit viewer. Add review moderation. Add a support ticket model and inbox. Replace settingsService, contentService and invoiceEmailService with real API calls. | Turns three orphan models into features
8 | Security Hardening | 4 days | HIGH | Add magic-byte image validation with Pillow and server-side resizing. Replace the in-process rate limiter with Redis. Add CSP, HSTS, Referrer-Policy and Permissions-Policy headers. Deduplicate the CORS allowlist and restrict origins to the deployed domain. Add structured logging with request correlation ids, Sentry error tracking and a database-aware health check. Remove seed_db.py hardcoded credentials. | Required before any public launch
9 | Automated Testing & CI | 5 days | HIGH | Add a SQLite fallback to TestingConfig and replace the raw DELETE FROM fixture with per-test transaction rollback. Complete coverage of payments (signature rejection, ownership, webhook verification, refund), the role matrix, stock concurrency and uploads. Add a .github/workflows/ci.yml running pytest, coverage, lint and the frontend build. Add a Playwright end-to-end test: register, add to cart, pay, receive an invoice, see the order. | Prevents every regression above
10 | Production Deployment & Integration | 7 days | CRITICAL | Replace mockRequest() in src/services/http.ts with fetch() and convert all 11 services to real API calls, one at a time, testing each. Prefix the API with /api/v1. Add a gunicorn entrypoint and delete run.py. Add a Dockerfile and docker-compose for app, PostgreSQL and Redis. Configure migrations on deploy, environment-based secrets, HTTPS, a process manager and database backups. Remove every mock service and the src/data seed files once converted. | The phase that makes it a product
DEFINITION OF DONE
Criterion | Current | Target | How it is measured
Backend starts from a clean clone | NO | YES | docker compose up then flask db upgrade, with no manual edits.
Full test suite runs in CI | NO | YES | pytest exits 0 on every pull request.
A user can register and verify by email | NO | YES | Playwright test.
A real payment is captured via Razorpay | NO | YES | Test-mode payment plus a verified webhook.
An invalid payment signature is rejected | NO | YES | Automated test asserting HTTP 400.
An invoice is generated, downloadable and emailed | NO | YES | Playwright test plus an inbox assertion.
A refund reaches Razorpay | NO | YES | Test asserting the refund payment_id is recorded.
No admin action goes unlogged | NO | YES | AuditLog row count equals the mutating-request count.
Frontend makes zero localStorage writes for domain data | NO | YES | grep for localStorage in src/services returns nothing.
debug is false and no dev server is exposed | NO | YES | gunicorn entrypoint; run.py deleted.

## Cloud Deployment
Cloud Deployment Readiness
You are deploying this to the cloud. This sheet states plainly what will happen on the first deploy attempt, and what must be built first for the architecture to actually work there. The current repository cannot be deployed successfully — it will not start.
DEPLOYABLE TODAY |  | CONTAINER / IaC |  | CI / CD | MANAGED SERVICES WIRED | BLOCKERS TO FIRST DEPLOY
NO |  | NONE |  | NONE | 0 of 6 | 9
WHAT WILL HAPPEN ON YOUR FIRST CLOUD DEPLOY TODAY
Step | Outcome | Why | Fix | Phase
1. Provision a container | PARTIAL | You can push a Python image, but there is no Dockerfile, so you would be writing one from scratch with no health check and no pinned dependencies. | Add a multi-stage Dockerfile with gunicorn. | Phase 10
2. Container starts | BROKEN | run.py forces DevelopmentConfig and debug=True on 0.0.0.0. In a container that exposes the Werkzeug debugger on a public interface, which is remote code execution. | Add a gunicorn entrypoint; never use run.py in a container. | Phase 10
3. Import the app | BROKEN | ModuleNotFoundError: No module named 'flask_migrate'. flask_jwt_extended, flask_bcrypt, marshmallow, flasgger, psycopg2, boto3 and razorpay are also missing, so the factory cannot be constructed. | Install the eight missing dependencies in requirements.txt. | Phase 1
4. Connect to managed Postgres | PARTIAL | The connection string comes from config.py, which falls back to a hardcoded URL rather than requiring DATABASE_URL. You will end up writing to whatever database the fallback names. | Require DATABASE_URL from the environment; fail fast if absent. | Phase 1
5. Run migrations | BROKEN | There is no alembic.ini, so flask db upgrade cannot run. Your excellent 369-line migration is stranded. | Add alembic.ini and run migrations as a release step, not at app start. | Phase 1
6. Serve traffic | PARTIAL | CORS is duplicated on config.py lines 43-44 and no CSP or HSTS is set, so the browser will be the first place the misconfiguration shows up. | Deduplicate CORS; add CSP and HSTS headers. | Phase 8
7. Accept an order | MISSING | The frontend calls no API. A deployed frontend and a deployed backend are two unrelated systems until mockRequest() is replaced with fetch(). | Cut the seam in src/services/http.ts, service by service. | Phase 10
8. Take a payment | BROKEN | razorpay is not installed, keys are empty, and the signature bypass means a payment could be confirmed without one. Deploying this would accept fraudulent orders. | Complete Phase 5 before any public hostname points here. | Phase 5
9. Confirm to the customer | MISSING | No email provider, no queue, no invoice, no PDF. A real order produces silence. | Complete Phase 6 before launch. | Phase 6
ARCHITECTURE CHECK — does the design fit the cloud?
Layer | Status | Assessment for cloud deployment | Recommended service | Severity
App server | MISSING | A Flask dev server is not a production server. It is single-threaded by default, has no graceful timeout handling and no worker recycling, so a memory leak takes the service down. | Gunicorn with gevent or gthread workers, behind a load balancer. | CRITICAL
Container image | MISSING | No Dockerfile. Without a pinned base image and a lockfile, two deploys of the same commit can behave differently. | Multi-stage Dockerfile, python:3.12-slim, non-root user. | CRITICAL
Managed Postgres | PARTIAL | The code is correct for managed Postgres — SQLAlchemy pooling, Alembic migrations, proper constraints. It has simply never been pointed at one. | RDS / Cloud SQL, with automated backups and a read replica only when needed. | HIGH
Connection pooling | MISSING | No PgBouncer and no pool size configuration. Under a few concurrent workers each opening its own pool, you will exhaust Postgres connections and the whole site will stall. | Set pool_size and max_overflow, and use PgBouncer in transaction mode. | HIGH
Redis | MISSING | No Redis anywhere, yet the rate limiter is in-process and email and PDF generation need a queue. Both are hard requirements for a multi-instance deploy. | ElastiCache / Memorystore, used for rate limits and as the Celery broker. | HIGH
Background worker | MISSING | No Celery. Sending email and generating invoices synchronously inside a request will eventually time out and lose the work. | A separate Celery worker deployment with its own autoscaling policy. | HIGH
Object storage | REAL | s3_service already implements genuine boto3 upload. This is the one cloud-shaped component that is ready. | S3, or an S3-compatible store such as Cloudflare R2 or MinIO. | LOW
Static frontend | PARTIAL | A Vite build can be hosted on any static host or CDN, but nothing configures the API base URL, so it cannot know where the backend is. | S3+CloudFront or a static host, with VITE_API_URL injected at build time. | HIGH
Secrets | PARTIAL | Secrets are git-ignored correctly, but config.py has hardcoded fallbacks that will silently mask a missing secret instead of failing the boot. | Secrets Manager / Key Vault, injected as environment variables, with no fallback values. | CRITICAL
TLS | MISSING | No HSTS, no certificate handling, no secure-cookie policy. TLS would have to terminate at the platform edge with nothing enforced in the app. | Terminate at the load balancer and add HSTS plus a redirect in the app. | HIGH
Health checks | PARTIAL | /health returns a static dict and never touches the database, so a platform liveness probe will report healthy while the app is broken. The probe must be fixed or it will route traffic into a dead container. | Liveness and readiness endpoints, with a real SELECT 1 in the readiness check. | CRITICAL
Auto-scaling | MISSING | No worker configuration and no capacity policy. The in-process rate limiter would also silently reset on every scale event. | Set min/max replicas and worker counts so the limiter is moved to Redis first. | MEDIUM
Logging & metrics | MISSING | No structured logs, no request correlation id, no metrics and no error tracking, so a cloud failure would be diagnosed by reading application prints. | CloudWatch / Cloud Logging, plus Sentry for exceptions and error-rate alarms. | HIGH
Migrations on deploy | BROKEN | No alembic.ini and no release step. Without a migration step, a new container serves code that expects columns the database does not have. | Run flask db upgrade as an explicit release job before the new version receives traffic. | CRITICAL
CI / CD | MISSING | No .github directory. Every deploy would be manual, so nothing verifies the build or runs the tests. | A CI workflow running pytest and the frontend build, then a gated deploy. | HIGH
Backups | MISSING | No backup or point-in-time-recovery configuration, and the Alembic baseline means there is exactly one schema and no tested restore. | Automated daily backups plus a quarterly restore drill. | HIGH
MINIMUM VIABLE CLOUD SETUP — target topology
Component | Status | Specification | Blocking gap | Phase
Load balancer + TLS | MISSING | HTTPS termination, HTTP redirect, health probe pointed at /health/ready. | No readiness endpoint that checks the database. | Phase 10
App service (2+ replicas) | MISSING | Gunicorn, 2-4 workers per replica, 2 replicas minimum, non-root container. | No Dockerfile, no gunicorn, no replica config. | Phase 10
Managed Postgres | PARTIAL | RDS PostgreSQL, automated backups, PITR enabled, connections via a pooler. | DATABASE_URL is not strictly required from the environment. | Phase 1
Redis | MISSING | Managed Redis for rate limits and as the Celery broker. | Entirely absent; the rate limiter is in-process. | Phase 6
Celery worker | MISSING | Separate worker service for email, PDF and webhook retry. | Entirely absent; work would run inside web requests. | Phase 6
Object storage | REAL | S3 bucket for product images with a CDN in front. | None — already implemented via boto3. | —
Static frontend | PARTIAL | Built Vite bundle on a CDN with VITE_API_URL injected at build time. | No API base URL configuration exists. | Phase 10
Secrets store | PARTIAL | All credentials in Secrets Manager, injected as env vars, no code fallbacks. | Hardcoded fallbacks on config.py lines 11-12 must go first. | Phase 1
Logging + alarms | MISSING | Structured logs, error tracking, and an alarm on 5xx rate and p95 latency. | No observability of any kind. | Phase 8
CI / CD pipeline | MISSING | Build, test, migration release job, then a gated rolling deploy. | No .github directory exists. | Phase 9
DEPLOY GATE — do not put a public hostname on this until all are YES
Gate | Current | Target | Why it is a hard gate | Phase
App imports without error | NO | YES | Eight missing dependencies. The container crash-loops today. | Phase 1
Migrations apply from alembic.ini | NO | YES | Without it the schema and the code will disagree in production. | Phase 1
No hardcoded secret fallbacks | NO | YES | A missing secret currently produces a publicly known key instead of a failed boot. | Phase 1
debug=False, gunicorn entrypoint | NO | YES | The interactive debugger on 0.0.0.0 is remote code execution. | Phase 10
Readiness probe checks the database | NO | YES | Otherwise the load balancer routes traffic to containers that cannot serve requests. | Phase 10
Invalid payment signature rejected | NO | YES | Otherwise a public URL accepts fraudulent payment confirmations. | Phase 5
Payment ownership enforced | NO | YES | Otherwise order IDs are guessable and payments are cross-account. | Phase 5
Webhooks signature-verified | NO | YES | An unauthenticated URL that credits orders is a direct revenue hole. | Phase 5
Email actually sends | NO | YES | Password reset and order confirmation are silently broken today. | Phase 6
Frontend calls the real API | NO | YES | Otherwise the deployed pair is two unrelated systems. | Phase 10
CI runs tests on every push | NO | YES | Nothing currently prevents a regression from reaching production. | Phase 9
Backups with a tested restore | NO | YES | One migration and no restore drill means data loss is unrecoverable. | Phase 9